## Slide 1: Comparison between PMBOK4 and PMBOK5
Created by:
Saqib Javed John
(PMP, ACP, ITIL, SCJP, SCWCD)

## Slide 2: High Level Comparison
PMBOK 4
Released in 2008
5 Process Groups
9 Knowledge Areas
42 Processes
PMBOK 5
Released in 2013
5 Process Groups
10 Knowledge Areas
47 Processes

## Slide 3: Addition in Knowledge Areas
PMBOK 4
Integration Management
Scope Management
Time Management
Cost Management
Quality Management
Human Resource Management
Communication Management
Risk Management
Procurement Management
PMBOK 5
Integration Management
Scope Management
Time Management
Cost Management
Quality Management
Human Resource Management
Communication Management
Risk Management
Procurement Management
Stakeholder Management

## Slide 4: Addition in Processes
PMBOK 4
 | I | P | E | M&C | C
Integration | 1 | 1 | 1 | 2 | 1
Scope |  | 3 |  | 2 | 
Time |  | 5 |  | 1 | 
Cost |  | 2 |  | 1 | 
Quality |  | 1 | 1 | 1 | 
Human Resource |  | 1 | 3 |  | 
Communications | 1 | 1 | 2 | 1 | 
Risk |  | 5 |  | 1 | 
Procurement |  | 1 | 1 | 1 | 1
Processes (42) | 2 | 20 | 8 | 10 | 2
PMBOK 5
 | I | P | E | M&C | C
Integration | 1 | 1 | 1 | 2 | 1
Scope |  | 4 |  | 2 | 
Time |  | 6 |  | 1 | 
Cost |  | 3 |  | 1 | 
Quality |  | 1 | 1 | 1 | 
Human Resource |  | 1 | 3 |  | 
Communications | 0 | 1 | 1 | 1 | 
Risk |  | 5 |  | 1 | 
Procurement |  | 1 | 1 | 1 | 1
Stakeholder | 1 | 1 | 1 | 1 | 
Processes (47) | 2 | 24 | 8 | 11 | 2
I=Initiation
P=Planning
E=Execution
M&E=Monitoring & Controlling
C=Closing

## Slide 5: Integration Management
 | Initiation | Planning | Execution | Monitoring & Controlling | Closing
PMBOK 4 | Develop Project Charter | Develop Project Management Plan | Direct & Manage Project Execution | Monitor & Control Project Work Perform Integrated Change Control | Close Project or Phase
PMBOK 5 | No Change and its same as in PMBOK4 |  |  |  | 

## Slide 6: Scope Management
 | Initiation | Planning | Execution | Monitoring & Controlling | Closing
PMBOK 4 |  | Collect Requirements Define scope Create WBS |  | Verify Scope Control Scope | 
PMBOK 5 |  | Plan Scope Management Collect Requirements Define scope Create WBS |  | Validate Scope Verify Scope Control Scope | 

## Slide 7: Time Management
 | Initiation | Planning | Execution | Monitoring & Controlling | Closing
PMBOK 4 |  | Define Activities Sequence Activities Estimate Activity Resources Estimate Activity Duration Develop Schedule |  | Control Schedule | 
PMBOK 5 |  | Plan Schedule Management Define Activities Sequence Activities Estimate Activity Resources Estimate Activity Duration Develop Schedule |  | Control Schedule | 

## Slide 8: Cost Management
 | Initiation | Planning | Execution | Monitoring & Controlling | Closing
PMBOK 4 |  | Estimate Costs Determine Budget |  | Control Costs | 
PMBOK 5 |  | Plan Cost Management Estimate Costs Determine Budget |  | Control Costs | 

## Slide 9: Quality Management
 | Initiation | Planning | Execution | Monitoring & Controlling | Closing
PMBOK 4 |  | Plan Quality | Perform Quality Assurance | Perform Quality Control | 
PMBOK 5 |  | Plan Quality Management | Perform Quality Assurance | Perform Quality Control Quality | 

## Slide 10: Human Resource Management
 | Initiation | Planning | Execution | Monitoring & Controlling | Closing
PMBOK 4 |  | Develop HR Plan | Acquire Project Team Develop Project Team Manage Project Team |  | 
PMBOK 5 |  | Develop HR Plan Plan HR Management | Acquire Project Team Develop Project Team Manage Project Team |  | 

## Slide 11: Communication Management
 | Initiation | Planning | Execution | Monitoring & Controlling | Closing
PMBOK 4 | Identify Stakeholders | Plan Communication | Distribute Information Manage Stakeholders Expectations | Report Performance | 
PMBOK 5 | Identify Stakeholders | Plan Communication Management | Distribute Information Manage Stakeholders Expectations Manage Communication | Report Performance Control Communication | 

## Slide 12: Risk Management
 | Initiation | Planning | Execution | Monitoring & Controlling | Closing
PMBOK 4 |  | Plan Risk Management Identify Risks Perform Qualitative Risk Analysis Perform Quantitative Risk Analysis Plan Risk Responses |  | Monitor and Control Risks | 
PMBOK 5 |  | Plan Risk Management Identify Risks Perform Qualitative Risk Analysis Perform Quantitative Risk Analysis Plan Risk Responses |  | Monitor and Control Risks Control Risks | 

## Slide 13: Procurement Management
 | Initiation | Planning | Execution | Monitoring & Controlling | Closing
PMBOK 4 |  | Plan Procurement | Conduct Procurements | Administer Procurement | Close Procurement
PMBOK 5 |  | Plan Procurement Management | Conduct Procurements | Administer Procurement Control Procurement | Close Procurement

## Slide 14: Stakeholder Management
 | Initiation | Planning | Execution | Monitoring & Controlling | Closing
PMBOK 4 | Stakeholder Management as a separate knowledge area was not the part of PMBOK4 |  |  |  | 
PMBOK 5 | Identify Stakeholder | Plan Stakeholder Management | Manage Stakeholder Engagement | Control Stakeholder Management | 

## Slide 15: Thanks……
Created by:
Saqib Javed John (MSc CS, PMP, ACP, ITIL v3F, SCJP, SCWCD
Email: saqib.jav@gmail.com
Skype: saqibjohn76
LinkedIn: pk.linkedin.com/pub/saqib-javed-john/b/125/1b1